## Pricing Summary
Safal S2C: Source-to-Contract Platform
Commercial proposal summary for Adani Group NextGen S2C ¦ Submitted by Safal Softcom Pvt Ltd, Ahmedabad ¦ All amounts in INR, exclusive of GST
Total investment, 5 years (INR crore) | Implementation (INR crore) |  | Subscription (INR crore) |  | Business Units covered
58.4705 | 19.0955 |  | 39.375 |  | 30
1. Five-year investment by year (INR)
Item | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total, 5 years
Platform Implementation, Customization & Configuration | 105305000 | 58200000 | 27450000 | 0 | 0 | 190955000
of which: Basic Platform & Customization (one time, 1st BU) | 44180000 | 0 | 0 | 0 | 0 | 44180000
of which: Project governance, delivery & integration resources | 61125000 | 58200000 | 27450000 | 0 | 0 | 146775000
Subscription Costs BU Wise (Unlimited User & Usage) | 22050000 | 78750000 | 94500000 | 99225000 | 99225000 | 393750000
Total (Implementation + Subscription) | 127355000 | 136950000 | 121950000 | 99225000 | 99225000 | 584705000
Implementation (INR crore) | 10.5305 | 5.82 | 2.745 | 0 | 0 | 19.0955
Subscription (INR crore) | 2.205 | 7.875 | 9.45 | 9.9225 | 9.9225 | 39.375
Total (INR crore) | 12.7355 | 13.695 | 12.195 | 9.9225 | 9.9225 | 58.4705
Cumulative investment (INR crore) | 12.7355 | 26.4305 | 38.6255 | 48.548 | 58.4705 | 58.4705
2. Business Unit rollout and subscription
| Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Business Units implemented in the year | 7 | 18 | 5 | 0 | 0 | 30
Business Units covered | BU 1 to 7 | BU 8 to 25 | BU 26 to 30 | - | - | BU 1 to 30
Business Units on subscription (cumulative) | 7 | 25 | 30 | 30 | 30 | 30
Annual subscription fee per Business Unit (INR) | 3150000 | 3150000 | 3150000 | 3307500 | 3307500 | 5% rise from Year 4
3. Year-wise investment (INR crore)
4. Scope of implementation and services included
Component | Person-months | Unit cost (INR) | Total (INR) | Engagement
Basic Platform & Customization (One Time) for 1st BU | 1 | 44180000 | 44180000 | One time, 1st BU
Project Governance & Transformation PMO (External) - 3 Resources - 9 Months (27 Person Months) | 27 | 575000 | 15525000 | 9 months
SAFAL Project Managers - 3 Resources - 24 Months (72 Person Months) | 72 | 350000 | 25200000 | 24 months
SAFAL Project Coordinators - 6 Resources - 24 Months (144 Person Months) | 144 | 175000 | 25200000 | 24 months
SAP Integration - 4 Persons - 30 Months (120 Person Months) | 120 | 350000 | 42000000 | 30 months
Ariba Integration - 1 Person - 24 Months (24 Person Months) | 24 | 275000 | 6600000 | 24 months
Lead Architect & Cloud Hosting - 1 Person - 30 Months (30 Person Months) | 30 | 525000 | 15750000 | 30 months
Other Integrations REST APIs - 2 Persons - 30 Months (60 Person Months) | 60 | 275000 | 16500000 | 30 months
UAT, SIT and Go-Live Training (Ahmedabad Location): included | - | - | - | Included
Hypercare Support from Ahmedabad Location (60 Days): included | - | - | - | Included (60 days)
Total implementation cost |  |  | 190955000
5. Subscription by Business Unit (INR)
Subscription by Business Unit | Starts in Year | Annual fee, Years 1 to 3 (INR) | 5-year total (INR) | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Business Unit 1 | 1 | 3150000 | 16065000 | 3150000 | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 2 | 1 | 3150000 | 16065000 | 3150000 | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 3 | 1 | 3150000 | 16065000 | 3150000 | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 4 | 1 | 3150000 | 16065000 | 3150000 | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 5 | 1 | 3150000 | 16065000 | 3150000 | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 6 | 1 | 3150000 | 16065000 | 3150000 | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 7 | 1 | 3150000 | 16065000 | 3150000 | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 8 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 9 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 10 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 11 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 12 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 13 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 14 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 15 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 16 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 17 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 18 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 19 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 20 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 21 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 22 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 23 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 24 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 25 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 26 | 3 | 3150000 | 9765000 |  |  | 3150000 | 3307500 | 3307500
Business Unit 27 | 3 | 3150000 | 9765000 |  |  | 3150000 | 3307500 | 3307500
Business Unit 28 | 3 | 3150000 | 9765000 |  |  | 3150000 | 3307500 | 3307500
Business Unit 29 | 3 | 3150000 | 9765000 |  |  | 3150000 | 3307500 | 3307500
Business Unit 30 | 3 | 3150000 | 9765000 |  |  | 3150000 | 3307500 | 3307500
Total Subscription Cost |  |  | 393750000 | 22050000 | 78750000 | 94500000 | 99225000 | 99225000
Total Cost (Implementation + Subscription) |  |  | 584705000 | 127355000 | 136950000 | 121950000 | 99225000 | 99225000
Total Cost in INR crore |  |  | 58.4705 | 12.7355 | 13.695 | 12.195 | 9.9225 | 9.9225
6. Payment terms at a glance (detailed schedule on the Payment Milestones sheet)
Component | Basis and milestones |  |  |  | Amount (INR) | Share of total
Basic Platform & Customization (one time) | Six milestones: 10% contract signing, 25% blueprint sign-off, 20% build and SIT, 20% UAT sign-off, 15% pilot go-live, 10% hypercare completion |  |  |  | 44180000 | 7.556%
Project governance, delivery & integration resources | Quarterly, in advance, in equal instalments over the engagement period |  |  |  | 146775000 | 25.1%
Subscription (unlimited users and usage) | Annually, in advance, at the start of each subscription year |  |  |  | 393750000 | 67.34%
Total contract value (5 years, excluding GST) |  |  |  |  | 584705000 | 100%
Invoice payment period: 30 days from invoice date, against the acceptance document.
7. Key commercial terms
• All prices are in Indian Rupees and are exclusive of GST and other applicable taxes, which are payable by Adani at the prevailing rate.
• Subscription covers 30 Business Units with unlimited users and usage. The fee per Business Unit is flat for Years 1 to 3, with a 5% increase from Year 4.
• UAT, SIT and go-live training, and 60 days of hypercare support from the Ahmedabad location, are included in the implementation price.
• Out-of-pocket expenses, if any, are billed at actuals with prior written approval and are not included in the amounts above.
• Business Units start subscription in the year they are implemented: 7 in Year 1, 18 in Year 2 and 5 in Year 3.
• Proposal validity: [CONFIRM] days from the date of submission.
Safal Softcom Pvt Ltd, Ahmedabad, India

## Price Proposal
Safal S2C: commercial proposal for Adani NextGen Source-to-Contract
30 Business Units over a 5-year term. All amounts in INR, exclusive of GST and other applicable taxes.
Platform Implementation, Customization & Configuration | Qty (person-months) | Unit Cost (INR) | Total (INR) | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Subscription inputs
Basic Platform & Customization (One Time) for 1st BU | 1 | 44180000 | 44180000 | 44180000 | - | NA | NA | NA | Annual fee per BU, Years 1 to 3 (INR) | 3150000
Project Governance & Transformation PMO (External) - 3 Resources - 9 Months (27 Person Months) | 27 | 575000 | 15525000 | 15525000 | - | NA | NA | NA | Escalation from Year 4 | 5%
SAFAL Project Managers - 3 Resources - 24 Months (72 Person Months) | 72 | 350000 | 25200000 | 6300000 | 12600000 | 6300000 | NA | NA | Escalation applies from year | 4
SAFAL Project Coordinators - 6 Resources - 24 Months (144 Person Months) | 144 | 175000 | 25200000 | 6300000 | 12600000 | 6300000 | NA | NA
SAP Integration - 4 Persons - 30 Months (120 Person Months) | 120 | 350000 | 42000000 | 16800000 | 16800000 | 8400000 | NA | NA
Ariba Integration - 1 Person - 24 Months (24 Person Months) | 24 | 275000 | 6600000 | 3300000 | 3300000 | NA | NA | NA
Lead Architect & Cloud Hosting - 1 Person - 30 Months (30 Person Months) | 30 | 525000 | 15750000 | 6300000 | 6300000 | 3150000 | NA | NA
Other Integrations REST APIs - 2 Persons - 30 Months (60 Person Months) | 60 | 275000 | 16500000 | 6600000 | 6600000 | 3300000 | NA | NA
UAT, SIT and Go-Live Training (Ahmedabad Location): included | - | - | - | - | - | NA | NA | NA
Hypercare Support from Ahmedabad Location (60 Days): included | - | - | - | - | - | NA | NA | NA
Total - Implementation Costs |  |  | 190955000 | 105305000 | 58200000 | 27450000 | 0 | 0
Total - Subscription Costs BU Wise (Unlimited User & Usage) |  |  | 393750000 | 22050000 | 78750000 | 94500000 | 99225000 | 99225000
Subscription basis: annual fee per BU, 5% escalation from Year 4 (inputs at right of this block)
Subscription by Business Unit | Starts in Year | Annual fee, Years 1 to 3 (INR) | 5-year total (INR) | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Business Unit 1 | 1 | 3150000 | 16065000 | 3150000 | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 2 | 1 | 3150000 | 16065000 | 3150000 | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 3 | 1 | 3150000 | 16065000 | 3150000 | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 4 | 1 | 3150000 | 16065000 | 3150000 | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 5 | 1 | 3150000 | 16065000 | 3150000 | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 6 | 1 | 3150000 | 16065000 | 3150000 | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 7 | 1 | 3150000 | 16065000 | 3150000 | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 8 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 9 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 10 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 11 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 12 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 13 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 14 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 15 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 16 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 17 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 18 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 19 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 20 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 21 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 22 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 23 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 24 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 25 | 2 | 3150000 | 12915000 |  | 3150000 | 3150000 | 3307500 | 3307500
Business Unit 26 | 3 | 3150000 | 9765000 |  |  | 3150000 | 3307500 | 3307500
Business Unit 27 | 3 | 3150000 | 9765000 |  |  | 3150000 | 3307500 | 3307500
Business Unit 28 | 3 | 3150000 | 9765000 |  |  | 3150000 | 3307500 | 3307500
Business Unit 29 | 3 | 3150000 | 9765000 |  |  | 3150000 | 3307500 | 3307500
Business Unit 30 | 3 | 3150000 | 9765000 |  |  | 3150000 | 3307500 | 3307500
Total Cost (Implementation + Subscription) |  |  | 584705000 | 127355000 | 136950000 | 121950000 | 99225000 | 99225000
Total Cost in INR crore |  |  | 58.4705 | 12.7355 | 13.695 | 12.195 | 9.9225 | 9.9225

## Payment Milestones
Payment milestones and invoicing schedule
A. Basic Platform & Customization (one time, 1st BU) | Indicative month | % of fee | Amount (INR) | Invoice trigger / acceptance evidence
1. Contract signing and project mobilisation | M1 | 10% | 4418000 | Signed contract / purchase order; project kick-off held
2. Business blueprint and design sign-off | M3 | 25% | 11045000 | Signed-off blueprint, fit-to-process and solution design documents
3. Build complete and System Integration Testing (SIT) passed | M5 | 20% | 8836000 | SIT exit report; zero open critical and high defects
4. User Acceptance Testing (UAT) sign-off | M6 | 20% | 8836000 | Signed UAT completion certificate from Adani
5. Pilot go-live | M7 | 15% | 6627000 | Go-live certificate; platform live in production for BU 1
6. Hypercare completion (60 days) | M9 | 10% | 4418000 | Hypercare exit report; closure of open items
Total, Basic Platform & Customization |  | 100% | 44180000 | OK: ties to Price Proposal
B. Resource-based services (PMO, project management, integration, architecture) | Basis |  | Amount (INR) | Invoicing
Year 1 resource services | Quarterly Advance |  | 61125000 | 4 equal quarterly invoices in advance, at the start of each quarter, against the approved resource plan
Year 2 resource services | Quarterly Advance |  | 58200000 | 4 equal quarterly invoices in advance
Year 3 resource services | Quarterly Advance |  | 27450000 | Quarterly invoices in advance until the resource plan completes
Total, resource-based services |  |  | 146775000 | OK: with A, ties to total implementation
C. Subscription (unlimited users and usage) | Basis |  | Amount (INR) | Invoicing
Year 1 subscription | Annual in advance |  | 22050000 | Invoiced at the start of each subscription year for the BUs starting or continuing in that year
Year 2 subscription | Annual in advance |  | 78750000 | Invoiced at the start of the year; BUs entering subscription are billed from their start year
Year 3 subscription | Annual in advance |  | 94500000 | Invoiced at the start of the year; BUs entering subscription are billed from their start year
Year 4 subscription | Annual in advance |  | 99225000 | Invoiced at the start of the year; BUs entering subscription are billed from their start year
Year 5 subscription | Annual in advance |  | 99225000 | Invoiced at the start of the year; BUs entering subscription are billed from their start year
Total, subscription |  |  | 393750000 | OK: ties to Price Proposal
Cash-out summary by year (INR) | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
A. Basic Platform & Customization | 44180000 | 0 | 0 | 0 | 0 | 44180000
B. Resource-based services | 61125000 | 58200000 | 27450000 | 0 | 0 | 146775000
C. Subscription | 22050000 | 78750000 | 94500000 | 99225000 | 99225000 | 393750000
Total invoiced | 127355000 | 136950000 | 121950000 | 99225000 | 99225000 | 584705000
General payment terms
1. Invoices are payable within 30 days of the invoice date, subject to receipt of the supporting acceptance document.
2. Milestone acceptance by Adani is deemed to be given if no written objection is raised within 10 working days of the deliverable being submitted.
3. All amounts are exclusive of GST and other applicable taxes, which are payable by Adani at the prevailing rate on each invoice.
4. Subscription fees for years 1 to 3 are held flat; a 5% escalation applies from year 4 as shown on the Price Proposal sheet.
5. Out-of-pocket expenses, if any, are billed at actuals with prior written approval and are not included in the amounts above.
6. Percentages, timing and billing frequency above are proposals for discussion and can be aligned with Adani procurement terms.

## Pricing Discussion
Adani 30-BU pricing discussion
Kep the same scope and original phased rollout: 7 / 25 / 30 cumulative BUs. INR excluding GST. Green highlights the +25% suggested discussion case.
Pricing basis | Original Ali pricing | Proposed +20% | Suggested +25% | Proposed +30%
Uplift applied to original quoted prices | 0% | 20% | 25% | 30%
Implementation, customization and configuration (INR)
Basic Platform & Customization (One Time) for 1st BU | 44180000 | 53016000 | 55225000 | 57434000
Project Governance & Transformation PMO (External) - 3 Resources - 9 Months (27 Person Months) | 15525000 | 18630000 | 19406250 | 20182500
SAFAL Project Managers - 3 Resources - 24 Months (72 Person Months) | 25200000 | 30240000 | 31500000 | 32760000
SAFAL Project Coordinators - 6 Resources - 24 Months (144 Person Months) | 25200000 | 30240000 | 31500000 | 32760000
SAP Integration - 4 Persons - 30 Months (120 Person Months) | 42000000 | 50400000 | 52500000 | 54600000
Ariba Integration - 1 Person - 24 Months (24 Person Months) | 6600000 | 7920000 | 8250000 | 8580000
Lead Architect & Cloud Hosting - 1 Person - 30 Months (30 Person Months) | 15750000 | 18900000 | 19687500 | 20475000
Other Integrations REST APIs - 2 Persons - 30 Months (60 Person Months) | 16500000 | 19800000 | 20625000 | 21450000
UAT, SIT and Go-Live Training (Ahmedabad Location): included | Included | Included | Included | Included
Hypercare Support from Ahmedabad Location (60 Days): included | Included | Included | Included | Included
Total implementation (INR) | 190955000 | 229146000 | 238693750 | 248241500
Subscription by business unit, five-year totals (INR)
Business Unit 1 | 16065000 | 19278000 | 20081250 | 20884500
Business Unit 2 | 16065000 | 19278000 | 20081250 | 20884500
Business Unit 3 | 16065000 | 19278000 | 20081250 | 20884500
Business Unit 4 | 16065000 | 19278000 | 20081250 | 20884500
Business Unit 5 | 16065000 | 19278000 | 20081250 | 20884500
Business Unit 6 | 16065000 | 19278000 | 20081250 | 20884500
Business Unit 7 | 16065000 | 19278000 | 20081250 | 20884500
Business Unit 8 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 9 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 10 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 11 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 12 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 13 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 14 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 15 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 16 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 17 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 18 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 19 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 20 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 21 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 22 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 23 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 24 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 25 | 12915000 | 15498000 | 16143750 | 16789500
Business Unit 26 | 9765000 | 11718000 | 12206250 | 12694500
Business Unit 27 | 9765000 | 11718000 | 12206250 | 12694500
Business Unit 28 | 9765000 | 11718000 | 12206250 | 12694500
Business Unit 29 | 9765000 | 11718000 | 12206250 | 12694500
Business Unit 30 | 9765000 | 11718000 | 12206250 | 12694500
Total subscription (INR) | 393750000 | 472500000 | 492187500 | 511875000
Total implementation + subscription (INR) | 584705000 | 701646000 | 730881250 | 760116500
Total implementation + subscription (INR crore) | 58.4705 | 70.1646 | 73.0881 | 76.0117
Annual implementation totals (INR)
Year 1 | 105305000 | 126366000 | 131631250 | 136896500
Year 2 | 58200000 | 69840000 | 72750000 | 75660000
Year 3 | 27450000 | 32940000 | 34312500 | 35685000
Year 4 | 0 | 0 | 0 | 0
Year 5 | 0 | 0 | 0 | 0
Annual subscription totals (INR)
Year 1 | 22050000 | 26460000 | 27562500 | 28665000
Year 2 | 78750000 | 94500000 | 98437500 | 102375000
Year 3 | 94500000 | 113400000 | 118125000 | 122850000
Year 4 | 99225000 | 119070000 | 124031250 | 128992500
Year 5 | 99225000 | 119070000 | 124031250 | 128992500
Annual combined totals (INR)
Year 1 | 127355000 | 152826000 | 159193750 | 165561500
Year 2 | 136950000 | 164340000 | 171187500 | 178035000
Year 3 | 121950000 | 146340000 | 152437500 | 158535000
Year 4 | 99225000 | 119070000 | 124031250 | 128992500
Year 5 | 99225000 | 119070000 | 124031250 | 128992500
Annual subscription per BU, Years 1–3 (INR) | 3150000 | 3780000 | 3937500 | 4095000
Annual subscription per BU, Years 4–5 (INR) | 3307500 | 3969000 | 4134375 | 4299750
Method: proportional commercial uplift across the same original implementation and subscription line items. Original quantities, scope classifications, 5% escalation from Year 4, milestone percentages and payment terms are unchanged.
The three original Ali tabs remain the unchanged baseline. The original 25-module SOW and its delivery classifications govern scope. No additional BUs or competitor line-item estimates are included. Separate infrastructure remains for Adani; the original quoted architecture/cloud-hosting line has not been expanded.
Annual implementation reconciliation (INR) | 0 | 0 | 0 | 0
Annual subscription reconciliation (INR) | 0 | 0 | 0 | 0
Annual combined reconciliation (INR) | 0 | 0 | 0 | 0
Illustrative hypercare value included in the proposal
Memo only. One illustrative 60-day team allocation, not per BU or rollout wave. INR excluding GST. This is not a discount, actual delivery cost or additional charge.
Illustrative role | Allocated FTE | Months | Quoted proxy / month (INR) | Included value proxy (INR)
Support engineers (Ariba / REST integration rate proxy) | 2 | 2 | 275000 | 1100000
Project coordinator | 1 | 2 | 175000 | 350000
Project manager (shared) | 0.25 | 2 | 350000 | 175000
Base team value proxy (INR) |  |  |  | 1625000
Illustrative planning reserve on quoted value | 20% |  |  | 325000
Total illustrative included value, with reserve (INR) |  |  |  | 1950000
Rate basis: Price Proposal C10 (engineer proxy), C8 (coordinator) and C7 (PM). These are quoted commercial rates, not verified hypercare labor costs. Validate role fit, staffing, coverage hours and resource availability.
The 20% reserve is an illustrative planning assumption applied to the quoted-value proxy. It is not demonstrated cost contingency or margin. Do not add this memo value to proposal totals, apply another uplift, or count already-budgeted PM / coordinator time twice.
Duration check: the current proposal includes 60 days from Ahmedabad. Any 90-day expectation needs explicit scope and staffing confirmation. This illustration does not price or commit the additional 30 days, multiple waves, on-site work or 24x7 coverage.
Commercial treatment: the value is included within the proposal, subject to validation. No incremental hypercare charge or separate discount is created by this matrix. Existing pricing scenarios and reconciliation checks remain unchanged.
Directional public benchmarks, not comparable supplier quotations
Supplier / documented service | Geography / scope | Published basis | Published rate | How to interpret
Safal hypercare illustration | Ahmedabad, India | 60-day allocation | Included | Memo value above
JAGGAER professional services | UK delivery | 8-hour day | GBP 1,125–1,800/day | Directional only [1]
Infosys: development / implementation and delivery / operation | Outside UK | 8.8-hour day | GBP 141–339/day | Directional only [2]
SAP Ariba support / initial assistance | Product / edition dependent | Subscription scope | Some support included | Not full hypercare [3]
The public rates cover different roles, locations, day lengths and services. They are not quotes for Adani, India or this hypercare team. “Outside UK” does not establish an India-specific rate. No currency conversion or competitor total is implied.
[1] JAGGAER G-Cloud 15 pricing, 2026: https://assets.applytosupply.digitalmarketplace.service.gov.uk/g-cloud-15/documents/92417/824695783438584-pricing-document-2026-01-29-1440.pdf
[2] Infosys G-Cloud 14 SFIA rate card, 2024: https://assets.applytosupply.digitalmarketplace.service.gov.uk/g-cloud-14/documents/93227/879049913464467-sfia-rate-card-2024-05-03-1559.pdf
[3] SAP Ariba onboarding: Current Generation includes initial deployment assistance. Next Generation is self-service with customer / partner deployment. Enterprise Support is included, not blanket project hypercare. https://support.sap.com/en/product/onboarding-resource-center/ariba.html
Rate-card limits: Infosys range covers only development / implementation and delivery / operation roles, not its full card. Both vendors specify weekdays excluding holidays. JAGGAER support / maintenance is included in access fees. Separate consulting services are scoped separately.